## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 63 | 0 | 68 |  |  | 48 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 0 | 0
| 2016-10-18 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Fri | Sat | Sat | Sat | Sat | Sat | Sat | Sun | Sun | Sun | Sun | Sun | Sun | Sun | Sun | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  | Hour: | 20:00 | 0:00 | 4:00 | 8:00 | 12:00 | 16:00 | 20:00 | 0:00 | 4:00 | 8:00 | 10:00 | 12:00 | 14:00 | 16:00 | 18:00 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
7 |  | Brainstorming | [23 empty] | Verify?
| 1 | Project Idea | ALL |  | 1 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | Mechanics | ALL |  | 1 | 0 | 1 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 |  | Sofa Gods | [23 empty] | Fixed
9 | 1 | Drop Couch | AL |  | 2 | 0 | 2 |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Deferred
10 | 1 | Cursor Grid Movement | SS | AL | 3 | 0 | 3 |  | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fact of Life
10 | 1 | Variable sofas | AL |  | 1 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fact of Life
10 | 1 | Recliner Catapult | AL |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fact of Life
11 | [25 empty] | Can't Repro
12 |  | Sofa Employees
13 | 1 | Player Movement | CP | YP | 4 | 0 | 3 |  | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | 1 | Respawn | CP |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | Shadow | YP |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | Points | CP | AL | 2 | 0 | 3 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 1 | Multiplayer Input | AL |  | 1 | 0 | 3 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 1 | Player movement constraints | SS |  | 1 | 0 | 3 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 |  | Layout
18 | 1 | Moving Screen | SS |  | 1 | 0 | 1 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 1 | Level Design | SS |  | 3 | 0 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 1 | Moving Camera | AL |  | 1 | 0 | 3 |  | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 1 | End Level | YP |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
20
Power Ups
| 3 | Players pick up powerups | CP |  | 1 | 0 | 2 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
22 |  | Visuals
23 | 1 | Employee | YP |  | 3 | 0 | 3 |  | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 1 | Couches | YP |  | 3 | 0 | 1 |  | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
33 | 2 | Lava | SS |  | 2 | 0 | 2 |  | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | Powerups | YP |  | 0.5 | 0 | 0.5 |  | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
25 |  | UI
21 | 3 | Menus | AL |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
21 | 1 | Points Display | AL |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | Tutorial | YP |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
26 |  | Sounds
28 | 2 | Background Music | SS |  | 2 | 0 | 2 |  | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
29 | 3 | Couch Drop | AL |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
30 | 3 | Celebration Music | AL |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
36 | 1 | Put it all together | ALL |  | 5 | 0 | 5 |  | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
37 | 1 | Playtesting | ALL |  | 6 | 0 | 6 |  | 6 | 6 | 5 | 5 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 0
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 | 1 | Different furnitures line up differently with the grid | SS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
108 | 1 | Camera renders lava on top of sofas | AL |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
109 | 1 | Infinite jumping | CP |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
110 | 1 | Players can push couches around | SS |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
112 | 1 | Make walls + sofas frictionless | YP |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 |  | Reported
113 | 1 | Replace second wall | YP |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 |  | Reported
114 | 1 | Disable sofa cursor movement | SS |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |  | Reported
115 | 1 | Place powerups | YP |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 |  | Reported
116 | 1 | Fix score display on endgame | CP |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 |  | Reported
117 | 1 | Change buttons on tutorial | AL |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | Reported
119 | [25 empty] | Reported
120 | [25 empty] | Reported
121 | [25 empty] | Reported
122 | [25 empty] | Reported
123 | [25 empty] | Reported
124 | [25 empty] | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 48 | 48 | 44 | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | 0 | 0 | 0
211 |  | Optimum | [5 empty] | Line | 63 | 63 | 57.75 | 52.5 | 47.25 | 42 | 36.75 | 31.5 | 26.25 | 21 | 15.75 | 10.5 | 5.25 | 0 | 0 | 0
212
213 |  | Sum | [6 empty] | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58 | 58
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 51.5 | 49.5 | 39.5 | 39.5 | 30.5 | 24.5 | 20.5 | 16.5 | 8.5 | 8.5 | 8.5 | 7.5 | 7.5 | 6.5 | 3.5 | 0
216 |  |  | 2 | [5 empty] | 6.5 | 4.5 | 3.5 | 3.5 | 2.5 | 2.5 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
217 |  |  | 3 | [5 empty] | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 0
218 |  |  | 4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Amy Liu | AL |  |  |  |  | AL | 11.5 | 11.5 | 8.5 | 8.5 | 7.5 | 5.5 | 5.5 | 3.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 0
223 |  | Chris Pike | CP |  |  |  |  | CP | 9.5 | 9.5 | 9.5 | 9.5 | 7.5 | 3.5 | 2.5 | 2.5 | 1.5 | 1.5 | 1.5 | 1.5 | 0.5 | 0.5 | 0 | 0
224 |  | Shane Schulte | SS |  |  |  |  | SS | 16 | 14.5 | 12 | 12 | 9 | 9 | 7 | 5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
225 |  | Yelena Pham | YP |  |  |  |  | YP | 12 | 11.5 | 7 | 7 | 6 | 6 | 4.5 | 3 | 3 | 3 | 3 | 3 | 3 | 1.5 | 0 | 0
226 |  | All | ALL |  |  |  |  | ALL | 13 | 11 | 10 | 10 | 7 | 7 | 6 | 6 | 4 | 4 | 4 | 3 | 3 | 3 | 2 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63 | 63
236

## Daily Scrum
Producer | 2016-10-18 |  | Team Members
Approved | Time |  | Amy Liu | Chris Pike | Shane Schulte | Yelena Pham | All
| 20:00 | Fri | Done: Brainstorming, spliting work Next: Sofa gods mechanics Help: | Done: Brainstorming game idea and mechanics, splitting work Next: Coding discrete player movement Help: Moving 3D people, jumping etc | Done: Brainstorming, created lava and wrote some code for camera Next: Start on music Help: | Done: Came up with game idea and began work on couches (loveseat) Next: loveseat, ottoman, L-shaped couch, 4-seater Help: | Done: Next: Help:
| 0:00 | Sat | Done: Dropping couches and movement Next: Rotating couches, detecting couches already below, multiplayer control setup, transparent aiming couch Help: | Done: Player movement Next: Help: | Done: Rudimentary music, could definitely be added to if there is time Next: Help: | Done: Finished couches Next: Making employee model Help: | Done: Next: Help:
| 4:00 | Sat | Done: Rotating couches, detecting couches, multiplayer control setup, transparent aiming couch Next: Help: | Done:Dying Next: Help: | Done: Added grid to sofa god cursor, started migrating things into the main scene Next: sleep Help: | Done: Made employee model in Blender Next: Import the model to Unity and get player movements working Help: | Done: Next: Help:
| 8:00 | Sat | Done: Sleep Next: Recliner, sofa god movement restraint, camera movement Help: | Done:Dead Next: Help: | tried to sleep | Done: Sleep (ish) Next: Help: | Done: Next: Help:
| 12:00 | Sat | Done: Recliner, sofa god movement polish, camera movement Next: Player Life UI Help: | Done:Dead Next: Help: | actually slept | Done: Player can move and jump, and colliding with couch of opponent causes player to slow down Next: Lives and end game Help: | Done: Next: Help:
| 16:00 | Sat | Done: Player Life UI Next: Multiplayer input Help: | Done: Alive Next: Player respawning Help: | woke up and got back to north | Done: Player shadows and end game scenes + platform Next: Help: | Done: Next: Help:
| 20:00 | Sat | Done: Multiplayer controller input Next: Bug fixes Help: | Done: Player respawning Next: Point Scoring Help: | Done: playtesting/bugfinding, started implementing level tutorial | Done: Background for menu, player shadows change y Next: Help: | Done: Next: Help:
| 0:00 | Sun | Done: Bug fixes Next: sleep Help: | Done: Reworked Spawning and point system Next: Reworking spawning and points, Playtesting Help: | Done: Finished 'tutorial' portion of the level, discussed stacking, bugfixing, ate wendy's Next: Figure out how to fix the physics interactions | Done: zzz Next: Help: | Done: Next: Help:
| 4:00 | Sun | Done: Next: Help: | Done: Playtesting Next: Sleep Help: | Done: forgot to sleep, fixed physics/enabled tetris mode, fixed some more bugs, added juiciness to couches dropping, helped rework player movement Next: sleep + sounds Help: | Done: zzz Next: Help: | Done: Next: Help:
| 8:00 | Sun | Done: sleep Next: Bug fixes, points UI, points pop up effect, playtesting Help: | Done: Sleep Next: Sleep Help: | g'night | Done: zzz Next: Help: | Done: Next: Help:
| 10:00 | Sun | Done: Bug fixes, playtesting, points UI Next: Menus Help: | Done: Sleep Next: Sleep Help: | zzzz | Done: Next: Help: | Done: Next: Help:
| 12:00 | Sun | Done: Menus Next: Recliner debugging Help: | Done: Sleep Next: Power ups Help: | Done: got back and caught up on everything that was done Next: Start bugfixing and playtesting Help: | Done: Created power-up assets and tutorial Next: Help: | Done: Next: Help:
| 14:00 | Sun | Done: Recliner debugging Next: Win screen points display, various UI tweaks Help: | Done: Power ups Next: More playtesting, throw away power ups Help: | Done: bugfix playtest (many times) Next: playtestplaytestplaytest Help: | Done: Made level design more complicated and longer Next: Help: | Done: Next: Help:
| 16:00 | Sun | Done:Win screen points display, various UI tweaks Next: Music and sound effects Help: | Done: Random bug fixes Next: Win screen final touches Help: | Done: playtest and tweaks Next: pray Help: | Done: added intro and powerups Next: Help: | Done: Next: Help:
| 18:00 | Sun | Done: Music and sound effects Next: Help: | Done: Everything Next: Hang out Help: | Done: woo Next: party Help: | Done: FINISHED GAME Next: Help: | Done: Next: Help: